## Sheet1
Execution Plan
Milestone | Assigned To | Week 1 24-Aug-20 | Week 2 31-Aug-20 | Week 3 7-Sep-20 | Week 4 14-Sep-20 | Week 5 21-Sep-20 | Week 6 28-Sep-20 |  | Week 7 5-Oct-20 | Week 8 12-Oct-20 | Week 9 19-Oct-20 | Week 10 26-Oct-20 | Week 11 2-Nov-20 | Week 12 9-Nov-20 | Week 13 16-Nov-20 | Week 14 23-Nov-20
Understand Project | All
Initial planning/research | All
Draft Conops Report | All
Source Lab Materials (Drone/Sensors) | All
Draft FSR Report | All
Draft ICD Report | All
Draft Exection Plan | All
Draft Validation Plan | All
Prepare Midterm Presentation | All
Design Server-Side Architecture | Jason
Remove Moving Obstacles from Data | Mark
Increase familiarity with Python | Max
Implement Sever-Side | Jason
Map Environment from Data | Mark
Create algorithm for valid accessible path | Max
Research/Order Parts | Dilanka/Jason
Create error handling for inaccessible path | Max
Implement Client-Side/UI | Jason
Estimate Depth on Path Sections | Mark
Research Drone SDK / stm32 / Sabretooth | Dilanka
Add flight mapping functionality | Jason
Research software interaction with drone | Max
Design Aerial/Land Electrical Schematics | Dilanka
Program manual override of drone | Max
Testing Electrical Off Drones | Dilanka
Merge Depth Estimates with Map | Mark
Build Air Drone | Dilanka
Build Land Drone | Dilanka
Prepare Status Update Presentation | All
Implement Server on drone | Jason
Test Flight of Air Drone | Dilanka
Normalize Depth Field for Drone Altitude | Mark
Program movement of drone | Max
Test Travel of Land Drone | Dilanka
Communicate with server on drone | Jason
Derive Gradient Field From Elevation Map | Mark
Program: Data Retreival of Air Drone | Dilanka
Test Drone Simulation Programs | Dilanka
Test Data Retreival From Drone | Dilanka
Implement Obstacle Delineation | Mark
Program drone path from map input | Max
Package Software/Create Installer | Jason
Prepare Final Presentaion | All
Test and modify Air system | Dilanka
Program: Autonomous Flight of Air Drone | Dilanka
Draft Final Report | All
Prepare Final Demo | All
Legend
Completed
Deadline
Planned Work Time
In Progress
Delayed